## SofGent Website Tasks
Task Name | Description | Priority | Status | Tags
[S0] Uncomment production GitHub Actions workflow | .github/workflows/production.yml is commented out. Uncomment, pin actions/checkout@v4, validate Vercel secrets, add PR preview + main deploy jobs. | 1 | to do | stage-0,devops
[S0] Replace static sitemap.xml with dynamic app/sitemap.ts | public/sitemap.xml lists non-existent routes that will 404 and hurt SEO. Delete the static file, generate via app/sitemap.ts from real routes + Sanity slugs, submit to Google Search Console. | 1 | to do | stage-0,seo
[S0] Run Lighthouse on key pages — hit 90/95/95/95 | Mobile targets for /, /services, /contact: Perf >= 90, A11y >= 95, Best Practices >= 95, SEO >= 95. Likely fixes: LCP hero image priority, gradient-text contrast, drop unused aos/parallax-js/tsparticles. | 1 | to do | stage-0,performance
[S1] Add trust strip above the fold — logos / metrics / testimonial | Zero social proof today. Render under hero one or all of: 4-6 greyscale client logos (anonymized if NDA), metrics strip (e.g. 1.2M docs processed, 80% manual work removed), or named testimonial with face + title. | 2 | to do | stage-1,design,conversion
[S1] Build flagship case study at /case-studies/[slug] | Structure: Client > Problem (1 para) > Architecture (SVG, not stock) > 3 outcome metrics > Timeline in days > Tech stack > CTO quote. The single highest-trust asset a studio can own. | 2 | to do | stage-1,content,design
[S1] Add real team section on /about | Real faces, real titles, real LinkedIn links. 'Led by Masud Alam — X years shipping AI systems at Y.' One real face beats ten stock icons. | 2 | to do | stage-1,content
[S1] Publish honest pricing range on site | One line: 'Engagements start at $15K. Typical AI product builds: $25K-$60K.' Filters tire-kickers, signals confidence, improves demo-call quality. | 2 | to do | stage-1,conversion
[S1] Replace Unsplash images on money pages | Every Unsplash image on home, services, and case studies > commissioned product screenshots or custom SVG architecture diagrams. Unsplash on a $50K studio site screams 'template'. | 2 | to do | stage-1,design
[S2] Rewrite hero as outcome + qualifier sub | Current: 'Build your AI product in 2-4 weeks' — generic. Better: 'Ship the AI product your roadmap has been stuck on — in 2-4 weeks.' Sub: 'Production-grade AI document automation, SaaS MVPs, and internal tools for fintech, legal, and ops teams. No prototypes. No tech debt.' | 2 | to do | stage-2,copy,conversion
[S2] Rename primary CTA to Book a 20-min Product Audit | 'Free Strategy Call' is overused. 'Book a 20-min Product Audit' sounds senior, outcome-specific, and converts better with CTOs. | 2 | to do | stage-2,copy,conversion
[S2] Add secondary CTA: AI Product Readiness Checklist lead magnet | Gated PDF: 'Get the SofGent AI Product Readiness Checklist'. Captures emails from not-ready-today visitors and feeds the list. | 2 | to do | stage-2,conversion,content
[S2] Rewrite 3 service cards as outcomes | Each card: outcome headline + timeline + deliverables + proof chip. Examples: 'Turn 1,000 PDFs into structured data in one sprint.' (Doc Intel) / 'Ship a revenue-ready SaaS MVP in 30 days.' (MVP) / 'Make legacy data AI-ready without a 6-month project.' (Data Eng). | 2 | to do | stage-2,copy
[S2] Add FAQ section with 6-8 questions on homepage | Cover: What is production-ready? / Pricing / Team size / IP ownership / Handling unclean data / Post-launch support / NDAs / Industries shipped. | 2 | to do | stage-2,content,conversion
[S2] Build embedded Calendly /book page | Embed the Calendly widget directly rather than linking out. Cuts clicks from homepage > meeting from 3 to 2. | 2 | to do | stage-2,conversion
[S2] Implement branded auto-reply email on form submit | Within 60 seconds of contact form submit, send branded confirmation with: receipt, SLA expectation (1 business day), lead-magnet PDF, Calendly backup link. | 2 | to do | stage-2,conversion,api
[S3] Enable Vercel Analytics + Speed Insights | Install @vercel/analytics and @vercel/speed-insights and wire to app/layout.tsx. | 3 | to do | stage-3,monitoring
[S3] Wire Sentry error tracking | Install @sentry/nextjs, set up DSN, test with a fake error. Essential before onboarding production clients. | 3 | to do | stage-3,monitoring
[S3] Add GTM conversion events for key CTAs | Events: book_call_click, contact_form_submit, lead_magnet_download. Wire Google Ads + LinkedIn conversion triggers if running paid. | 3 | to do | stage-3,analytics
[S3] Add JSON-LD Organization + Service + WebSite schema | Ship structured data in app/layout.tsx + service pages. Boosts SERP rich results. | 3 | to do | stage-3,seo
[S3] Ship branded app/not-found.tsx 404 page | Custom 404 with header/footer, 'Looking for…' nav, and a CTA back to /services. | 3 | to do | stage-3,design
[S3] Add cookie consent banner for GDPR | If any EU traffic, a cookie banner is legally required because GTM + analytics fire non-essential cookies. Use Cookiebot or a simple in-house banner. | 3 | to do | stage-3,legal
[S3] Pick Sanity OR Keystatic — remove the other | Repo has both sanity/ and keystatic.config.ts. Two CMSes is a trust smell to technical buyers reading the repo. Pick one, migrate content, delete the other. | 3 | to do | stage-3,tech-debt
[S3] Cross-device smoke test (mobile + tablet + desktop) | Manually verify rendering on iOS Safari, Android Chrome, iPad Safari, macOS Chrome + Safari, Windows Chrome. Fix any layout regressions. | 3 | to do | stage-3,qa
[S3] Run 3 think-aloud tests with ICP prospects | 5-minute user tests with 3 target-customer-profile people (fintech CTO / ops lead / founder). Fix top 3 friction points they surface. | 3 | to do | stage-3,research
[S4] Write pillar article: Document intelligence pipeline | Target keyword: 'document intelligence pipeline architecture'. 1,500-2,500 words, real diagram, real code snippet, CTA to book. | 3 | to do | stage-4,content,seo
[S4] Write pillar article: 2-week AI MVP playbook | Target: non-technical founders. How SofGent ships AI MVPs in 2 weeks, with a real project timeline. | 3 | to do | stage-4,content,seo
[S4] Write pillar article: Legacy data > AI-ready in 30 days | Target: enterprises / operations leads preparing data for AI adoption. Real architecture, 30-day plan. | 3 | to do | stage-4,content,seo
[S4] Write flagship article: Why AI prototypes never reach production | Opinionated long-form. The piece that gets reshared on LinkedIn by CTOs. Link every service page to it. | 3 | to do | stage-4,content
[S4] Publish gated case-study PDFs | Each case study > downloadable PDF behind email capture. Gets reshared inside prospect companies. | 3 | to do | stage-4,content,conversion
[S4] Build comparison pages: SofGent vs Dev Shop, vs In-House AI Team | Mid-funnel conversion pages. Structured as side-by-side tables with honest pros/cons. | 3 | to do | stage-4,content,conversion
[S4] Set up LinkedIn auto-reshare pipeline | Every new article > Buffer/Taplio schedule or manual weekly reshare. Drives traffic back to the site. | 3 | to do | stage-4,distribution
[S4] Submit 2 guest posts to fintech/ops publications | Publications where your buyers already read (e.g. Fintech Today, Operations Leader, industry newsletters). Backlinks to /case-studies for SEO lift. | 3 | to do | stage-4,distribution,seo
[S5] Record Loom explainer video for hero (15-30s) | 'Hi, I'm Masud. Here's what SofGent builds.' Real face + voice above the fold lifts conversion 2-3x. | 4 | to do | stage-5,design,content
[S5] Design 1-page capabilities PDF sales sheet | Polished PDF mirroring site branding. Attached to every cold email. Lists services, outcomes, pricing range, case-study teasers. | 4 | to do | stage-5,sales,design
[S5] Update LinkedIn company cover + pinned post | Cover reinforces the site hero. Pinned post links to the flagship case study. | 4 | to do | stage-5,distribution
[S5] Draft cold-email template library (founder/CTO/ops variants) | 3 variants. Each ends linking a specific case study, not the homepage. | 4 | to do | stage-5,sales
[S5] Build referral landing page for past clients | Shareable link with pitch + Calendly. One page past clients can forward to peers who need AI/SaaS help. | 4 | to do | stage-5,conversion
[S5] Install Meta + LinkedIn retargeting pixels | Pixel on homepage > 3-ad retargeting sequence (case study > testimonial > last-call offer) for visitors who don't book. | 4 | to do | stage-5,growth,analytics